## Sheet1
Section | Item No. | Title | Details | Status
Appointment & Photo Functionality Updates | 1 | Photo Functionality Based on Group Size | If the group has more than 10 people, photo functionality should be disabled. If the group has 10 or fewer people, photo functionality should be enabled.
Appointment & Photo Functionality Updates | 2 | AOL Field | Remove AOL field from the appointment section. In the “Request Appointment (Myself)” form, the AOL Teacher selection should be dynamic, with options: No, Part-Time, and Full-Time.
Appointment & Photo Functionality Updates | 3 | Teacher Verification | Once a teacher is verified, the edit functionality should be disabled. Teacher verification section should be displayed at the top.
Divine Pic (Photo Display) Enhancements | 4 | Photo Display(Divine Pic) | All uploaded photos should be visible from the user side under Divine Pic. Include “Darshan Photos with Gurudev” functionality within Divine Pic. Add Digi Yatra-style instructions under Divine Pic.
UI & UX Improvements | 5 | Edit Options | Edit icon should be placed on the right side. Save and Delete buttons should be positioned at the bottom.
UI & UX Improvements | 6 | Sidebar and Counts | Add appointment counts to the sidebar: Morning = 0, Evening = 0, Night = 0, TBS/Req = 0. in new application
UI & UX Improvements | 7 | Search and Filters | Search bar is missing – needs to be added. Filter functionality is currently not working – needs to be fixed.
UI & UX Improvements | 8 | Appointment Behavior | When an appointment is updated and saved, it should automatically move to the top of the list. Update the link for upcoming appointments (ensure it’s correctly mapped).
UI & UX Improvements | 9 | Headers and Labels | Remove “Accompany User” header. Replace “Checked-in Partial” with 'Admitted', and show it in green color. Update “No Users Found” to “No Accompany Users”.
UI & UX Improvements | 10 | Indexing in Guard View (Mobile App) | On the appointment detail screen for guards, each user should have an index number, e.g., 1. Avinash Gamit.
Communication & Email Features | 11 | CC & BCC | The CC and BCC email functionalities are not working and need to be fixed.
Communication & Email Features | 12 | Bulk Email | Bulk email functionality needs to be updated and tested.
Secretary Names & Miscellaneous | 13 | Secretary Updates | Add two more secretary names: Karthika and Krishna.
Secretary Names & Miscellaneous | 14 | Delete Functionality | Delete and Delete Bin features are currently not working – fix required.